Certificate Process and Estimate Timetable

Certificate Process

| Stage | Description | Description (Chinese) |
| --- | --- | --- |
| Step 1 | Manufacture Questionnaire | 填写生产商问卷表 |
| Step 2 | Quotation and Agreement | 给出报价、签署协议 |
| Step 3 | Manufacture Review | 工厂审核 |
| Step 4 | Sample Selecting and Testing | 样品选择和检测 |
| Step 5 | Apply and Get GREENGUARD Certificate | 申请并获得GREENGUARD认证 |
|  | Quarterly Test and Annual Review | 季度抽检和年度续认证 |

Estimate Timetable

| Serial # | Description | Estimate Time | Handle | Note |
| --- | --- | --- | --- | --- |
| 1 | Matrix communication (document for manufacturer review) | one week | Manufacture / GREENGUARD | Supposed can startup on next Monday, June 15th |
| 2 | Manufacturer review | one or two working days per Mill | GREENGUARD | 3 or 4 working days for QiangLong and Concept |
| 3 | Matrix complete (document for manufacturer review) | one week | Manufacture / GREENGUARD |  |
| 4 | Profile study test material selecting and communication | one week | GREENGUARD / Manufacture |  |
| 5 | Profile study test material preparation | one week | Manufacture |  |
| 6 | Sample shipping | one week | Manufacture | Within 7 days |
| 7 | Profile study test and report | one month | AQS Lab |  |
| 8 | Certificate test product selection and communication | one week | GREENGUARD / Manufacture |  |
| 9 | Certificate test product preparation | one week | Manufacture |  |
| 10 | Sample shipping | one week | Manufacture | Within 7 days |
| 11 | Certificate test and report | one month | AQS Lab |  |
| 12 | Apply and get GREENGUARD certificate | one working day | GREENGUARD | Supposed can be accomplished on Oct 15th. |

* All above is a rough time line, not include any special case. If there is any change of time in the process, the expected date will be changed.