Certification Process and Timetable

Process

| Steps | Description |
| --- | --- |
| 1 | Complete Manufacturing Questionnaire |
| 2 | Provide Quotation for Certification |
| 3 | Sign Agreement |
| 4 | Initial Payment of Certification Funds |
| 5 | Manufacturing Review |
| 6 | Select Samples and Testing |
| 7 | GREENGUARD Certification Testing |
| 8 | After successful tests and payment of final certification fee, the GREENGUARD Certification is issued. |
| 9 | Quarterly Test and Annual Review |

Timetable

| Step | Description | Estimated Time | Responsible |
| --- | --- | --- | --- |
| 1 | Product Matrix Communication (preparation for manufacturer review) | 1 week | Manufacturer / GREENGUARD |
| 2 | Manufacturer review | 1 or 2 working days per location | GREENGUARD |
| 3 | Matrix complete (document for manufacturer review) | 1 week | Manufacturer / GREENGUARD |
| 4 | Profile study test material selection | 1 week | GREENGUARD / Manufacturer |
| 5 | Profile study test material preparation | 1 week | Manufacturer |
| 6 | Ship Samples | 1 week | Manufacturer |
| 7 | Profile study test and report | 1 month | AQS Lab |
| 8 | Certification “test product” selection and communication | 1 week | GREENGUARD / Manufacturer |
| 9 | Certification “test product” preparation | 1 week | Manufacturer |
| 10 | Ship Samples | 1 week | Manufacturer |
| 11 | Certification testing and report issued | 1 month | AQS Lab |
| 12 | GREENGUARD certification | 1 working day | GREENGUARD |